## Sheet1
Product Backlog
Priority | Product Backlog Items | User Story # | User Story | Story Point (Difficulty) | Estimate (Hours) | Member Assigned To
1 | Database Creation | 13 | As a product owner, I want to have a database so that I can save user data. | 8 | 8 | Savannah
2 | Create Login Page | 5 | As a user I want to login to the site so that I can access my page. | 2 | 2 | Larissa
3 | Account Registration | 6 | As a user I want to register an account on the website so that I can login | 3 | 3 | Joe
4 | Search Image | 1 | As a user I want to be able to search up an image on the website so that It can be used as my background on the Website. | 5 | 5 | Mitchell
5 | Same image check | 4 | As a user I don't want to see the same image twice so that I don't get bored | 13 | 13 | Savannah
6 | Save Image | 7 | As a user I want to save images that I like so that I can select those as a background again later. | 13 | 13 | Mitchell
7 | Skip Background | 8 | As a user, I want to be able to skip background images I do not like so that I no longer have to see that image. | 3 | 3 | Seth
8 | Never See Skips | 14 | As a user, I want to be able to not see skipped background images, so that I no longer have to see that image in the future | 20 | 20 | Joe
9 | Download Image | 12 | As a user, I want to be able to download the image to my computer so that I can access the picture without accessing the website. | 3 | 3 | Mitchell
10 | Pixelate Image | 3 | As a user I want to be able to pixelate an image so that this changes my background image. | 3 | 3 | Larsissa
11 | Select Image | 2 | As a user I want to be able to select widgets that are visible so that my dashboard is customizable. | 8 | 8 | Joe
12 | Drag Widgets | 9 | As a user, I want to be able to drag widgets from a bank to the main screen to use it so that my page is easily customizable. | 40 | 40 | Seth
13 | Automatic Saving | 11 | As a user, I want the page to automatically save when I move or add widgets, and save new backgrounds to my favorites so that I do not have to repeat my actions later. | 40 | 40 | Tracen
14 | Save Widget Selection | 10 | As a user, I want my selected widgets to be saved for the next time I log in so that I do not have to select them again. | 13 | 13 | Savannah