## Sheet1
Sprint 1 Design
Priority | Sprint Items | User Story # | User Story | Story Point (Difficulty) | Estimate (Hours) | Member Assigned To
1 | Database Creation | 13 | As a product owner, I want to have a database so that I can save user data. | 8 |  | Savannah
The software developer will create an ER Diagram of the database.
The agile team shall go over the ER diagram
The software developer shall code the database
The software developer shall fill the database with test data.
The software developer shall create a series of tests.
The software developer shall debug the database
All test shall pass
learning and install time
2 | Create Login Page | 5 | As a user I want to login to the site so that I can access my page. | 2 | 2 | Mitchell
Create a HTML page for the login page
create two text entry boxes for Username and Password and a button for new user registration.
link text entry boxes with database for user look-up.
If not a user, ask for re-entry of data in case of errors inputing. If user found, redirect to website home page.
3 | Create Website Home Page | 16 | As a user, I want to have a home page where all my widgets are contained and my background image is displayed. | 2 | 2 | Larissa
Create HTML page for the homepage.
Make background an image from database.
Make a textbox with a welcome message.
4 | Account Registration | 6 | As a user I want to register an account on the website so that I can login | 3 | 3 | Joe
Create account registration HTML page with fields required to make an account.
Create link on login page to route to registration page.
Verify data inputted into registration page by checking for existing email and username.
Integrate emailing into project.
Send a link to provided email if verification passes.
Prevent form from submitting if verification fails and inform user which fields need to change.
Once registration link is click, account becomes verified in database.
5 | Search Image | 1 | As a user I want to be able to search up an image on the website so that It can be used as my background on the Website. | 5 | 5 | Seth
Create a text box to enter the search criteria for the image search. save the entered data.
Use the user text that was entered as a search parameter for the image search.
Find a website that has free high-quality wallpapers that can be searched with a description such as what the user will enter and a size option so that we can match the user's screen and the image found.
Figure out the User's screen size.
Return an image from the website and set it as the user's background on our website.
6 | Same image check | 4 | As a user I don't want to see the same image twice so that I don't get bored | 13 | 13 | Tracen
Create image bank of disliked images
Modify search for photo function to check disliked image bank before choosing image.
Set timeframe to wipe disliked image bank